## Sheet1
CONSTRUCTION OF WASTE MANAGEMENT CENTRE - GA. NILANDHOO
Bill of Quantities
| Length of Collection Bay Area | 23.2
| Width of Collection Bay Area | 4.3
| Total length of Collection Bay Area 3.5m high walls | 41.9
| Number of G.I Pipe Columns in Collection Bay Area | 10
| Number of RC Columns in Collection Bay Area | 13.9667
| Total length of Collection Bay Area 1.5m high walls | 16
| Total length of Perimeter Wall | 79.5
| Number of Columns in Perimeter Wall | 39.75
| Length of Compost Slab | 15
| Width of Compost Slab | 8
| Length of Concrete Screed | 0
| Width of Concrete Screed | 0
No | Item | Unit | Quantity | Rate | Amount
1 | Preliminaries
1.1 | Mobilization to site | LS | 1
1.2 | Site management cost including set up of temporary services for contractor's services as maybe necessary | LS | 1
2 | Site Clearance and Demolition/Removal
2.1 | All site clean up work | LS | 1
Demolition
2.2 | demolition of slab a top collection bay area bay 3 walls | LS | 1
3 | Earth works
Allow for all excavation work for foundations as follows
3.1 | Collection bay column foundation | m3 | 0.165
4 | Concrete works
Collection Bay Area
4.1 | Concrete column for sorting area platform cast according to drawing. | m3 | 0.612
4.2 | Provide 150mm thick reinforced concrete slab for sorting area platform cast according to drawing. Reinforcements shall be as shown on drawing. | m3 | 0.72
Compost Slab
Other
4.3 | Foundation for flood light pole | m3 | 0.288
5 | Structural steel works
Collection Bay Area
5.1 | Provide 75mm G.I pipe as structural columns for collection bay area. Rate shall include cutting and removal od prtion of wall,demolition of floor slab as required, reinstating the aforementioned and all fixings at both ends of the pipe for necessary connections as shown on drawing | Nos | 4
5.2 | Provide truss as shown on the drawing. Rate shall include all cuttings, weldings, applying of protective coating for welded joints, and setting up the truss | m | 8.15
Perimeter Wall
5.3 | Provide 75mm G.I pipe as flood light fixing poles. Rate shall include installation charges as shown on drawing. | Nos | 2
6 | Painting works
Collection Bay Area Walls
6.1 | Apply emulsion paint coating on 3500mm high walls for Collection Bay Outer Walls | m2 | 319.12
6.2 | Apply emulsion paint coating on 1500mm high walls for Collection Bay section separation | m2 | 51.3
Collection Bay Area Steel Members
6.3 | Apply emulsion paint coating on G.I columns of collection bay | LS | 1
6.4 | Apply emulsion paint coating on the roof trusses | LS | 1
6.5 | Apply paint coating on the metal sliding door of the Hazardous waste storage room | LS | 1
6.6 | Apply paint coating on the two metal folding doors of the equipment room | LS | 2
Perimeter Wall
6.7 | Apply emulsion paint coating on 1000mm high wall for perimeter fence | m2 | 171.825
Perimeter Wall Steel members
6.7 | Apply emulsion paint coating on G.I members of perimeter fence | LS | 1
6.9 | Apply emulsion paint coating on G.I members and MS Sheets of gates | LS | 1
Other
6.1 | Apply paint coating on flood light pole | LS | 2
6.11 | Apply emulsion paint coating on the removable timber covers of the leachate collection tanks | LS | 2
6.12 | Apply emulsion paint coating on 2000mm high walls of thickness 150mm for Pump House (1700mm high wall above ground level with 300mm below ground level) | m2 | 12.58
Existing Structure
6.13 | Apply emulsion paint coating on G.I columns of existing structure | LS | 1
6.14 | Apply emulsion paint coating on 2m high walls of the existing structure | m2 | 58.1
7 | Roofing works
Collection Bay Area
7.1 | Dismantling and reinstating of roof as per drawing to replace roof timber structure. | m2 | 111.36
8 | Electrical works
Collection Bay Area
8.1 | Provide 3 phase 13 A power sockets in equipment room. Rate shall include connection to circuit breaker and all necessary accessories | Nos | 4
8.2 | Provide 100W ceiling mount energy saving light in equipment room, provide the switches near circuit breaker inside the equipment room. Rate shall include connection to circuit breaker | Nos | 1
8.3 | Provide 100W ceiling mount energy saving light in hazardous waste storage room, provide the switches near circuit breaker inside the equipment room. Rate shall include connection to circuit breaker | Nos | 1
8.4 | Provide and mount a Ceiling fan inside the Equipment Room as indicated. Rate shall include provision of switch near the circuit breaker inside the equipment room, connection to circuit breaker and all necessary accessories | Nos | 1
8.5 | Supply and fix electric meter, 4 pole MCCB, Single Phase distribution board and 3 Phase distribution board as shown on drawing. Earth link and connection to earth rod with proper earth pit should be provided as well | LS | 1
8.6 | Provide and mount a exhaust fan inside the Equipment Room and Hazardous Waste Storage Room. Rate shall include provision of switch near the circuit breaker inside the equipment room, connection to circuit breaker and all necessary accessories | LS | 2
8.7 | Provide weather proof switch for all lights | LS | 1
8.8 | Provide 25 sqmm 4 core power supply cable from nearest distribution box to waste yard distribution board | m | 150
Other
8.9 | Provide 13 A power socket for well water pump inside the Pump House, provide the switch for the pump near circuit breaker inside the equipment room. Rate shall include connection to circuit breaker. | Nos | 1
8.1 | Provide 200 W flood light for illuminating the waste yard. Rate shall include connecting each light to a switch near circuit breaker inside the equipment roomand providing power to the switch | Nos | 2
8.11 | Provide well water pump. Rate shall include its fixing inside the Pump House | Nos | 1
9 | Plumbing works
9.1 | Provide connection from pump to ground water well. Rate shall include all necessary pipes, bends, fittings and footvalve and others as maybe required. | LS | 1
9.2 | Provide outlet pipes as shown on drawing. Rate shall include connection to pump, bends, fittings and others as maybe necessary. | LS | 1
9.3 | Provide PVC taps at ends of outlet pipes. | Nos | 2
9.4 | Supply 25mm diameter flexible hose | m | 25
10 | Doors and windows
Metal Doors
10.1 | Provide lockable metal sliding gates for entrance to hazardous waste storage room. Rate shall include all cuts, welds, applying protective coating to welded joints, painting the door and proper fixing of the door. Rate shall include fabrication and fixing of guide rails and wheels as well. | Nos | 1
10.2 | Provide lockable metal folding gates for entrance to Equipment room. Rate shall include all cuts, welds, applying protective coating to welded joints, painting the door and proper fixing of the door. Rate shall include fabrication and fixing of guide rails and wheels as well. | Nos | 2
10.3 | Provide lockable metal gates for entrance to waste yard as specified in the drawing. Rate shall include all cuts, welds, applying protective coating to welded joints, painting the frame and properly fixing the door to the fence. | Nos | 2
Timber Doors
10.4 | Provide a lockable timber door of dimensions 1000mm x 1000mm with double door frames and fixed timber louvers for the ground water pump room hut. Rates shall include all materials, hinges and fixings. | Nos | 1
11 | Other Works
Collection Bay Area
11.1 | Provide a 5" vinyl roof gutter with 2" x 3" downspout. Rates shall include all materials and fastenings. | LS | 1
11.2 | Provide 12" x 12" ceramic tiles for the top and the sides of the concrete slab for sorting area platform | m2 | 6.6
Perimeter Wall
11.3 | 50 x 50 PVC coated mesh. Rate shall include properly securing the mesh to G.I steel frame | m2 | 166.95
Compost Slab
11.4 | Provide HDPE membrane below compost slab, Concrete screed and collection bay floor slab | m2 | 219.76
11.5 | Provide expansion joint in slab and fill the joint with polyethylene joint filler form and silicone as shown on drawing | m | 24
11.6 | Provide two timber removable covers for the leachate collection tank of size 1000x2000mm. Rates shall include all materials, fastenings and handles. | LS | 2
11.7 | Connection of compost slab drain to primary tank of the leachate tank including ball valve | LS | 1
11.8 | Leachate collection tank overflow from primary to secondary tank as shown. | Nos | 1
12 | Demobilisation Works
12.1 | Setup sign boards on site as specified | LS | 1
12.2 | Clean up site upon completion of works | LS | 1
12.3 | Demobilization | LS | 1
TOTAL

## Sheet2
CONSTRUCTION OF WASTEMANAGEMENT CENTRE - GA. NILANDHOO
Bill of Quantities
SUMMARY SHEET
Bill No | Item | Amount
1 | Preliminaries
2 | Site clearance/Demolition/Removal
3 | Earth works
4 | Concrete works
5 | Structural steel works
6 | Masonary works
7 | Plastering works
8 | Painting works
9 | Roofing works
10 | Electrical works
11 | Plumbing works
12 | Doors and windows
13 | Other Works
14 | Demobilisation
Sub Total
GST 6%
GRAND TOTAL

## LD
CONSTRUCTION OF WASTE MANAGEMENT CENTRE - GA. NILANDHOO
Bill of Quantities
| Length of Collection Bay Area | 23.2
| Width of Collection Bay Area | 4.3
| Total length of Collection Bay Area 3.5m high walls | 41.9
| Number of G.I Pipe Columns in Collection Bay Area | 10
| Number of RC Columns in Collection Bay Area | 13.9667
| Total length of Collection Bay Area 1.5m high walls | 16
| Total length of Perimeter Wall | 79.5
| Number of Columns in Perimeter Wall | 39.75
| Length of Compost Slab | 15
| Width of Compost Slab | 8
| Length of Concrete Screed | 0
| Width of Concrete Screed | 0
Completed at termination
No | Item | Unit | Quantity | Rate | Amount |  |  |  | Qty | Amount
1 | Preliminaries
1.1 | Mobilization to site | LS | 1 | 5000 | 5000 |  |  |  | 1 | 5000
1.2 | Site management cost including set up of temporary services for contractor's services as maybe necessary | LS | 1 | 2500 | 2500 |  |  |  | 0.5 | 1250
[5 empty] | 7500 |  |  |  |  | 0
2 | Site Clearance and Demolition/Removal | [8 empty] | 0
2.1 | All site clean up work including relocation of existing waste to a temporary location identified by island council | LS | 1 | 2500 | 2500 |  |  |  | 1 | 2500
| Demolition | [8 empty] | 0
2.2 | Concrete column foundation 450x450mm of height 400mm | LS | 20 | 250 | 5000 |  |  |  |  | 0
2.3 | 2000mm high masonry walls | m | 7.4 | 500 | 3700 |  |  | 3700 | 7.4 | 3700
| Removal | [8 empty] | 0
2.4 | G.I Pipe fence of height 2000mm with 50mm Mesh as shown in the drawing | m | 60 | 25 | 1500 |  |  |  |  | 0
[5 empty] | 12700 |  |  |  |  | 0
3 | Earth works | [8 empty] | 0
| Allow for all excavation work for foundations as follows | [8 empty] | 0
3.1 | Collection bay foundation | m3 | 4.8945 | 150 | 2200.5 |  |  |  |  | 0
3.2 | Perimeter wall | m3 | 8.3475 | 150 | 3757.5 |  |  |  |  | 0
3.4 | Flood light pole | m3 | 0.128 | 150 | 58.5 |  |  |  |  | 0
3.5 | Ground levelling works for ground slab works | m2 | 219.76 | 35 | 15383.2 |  |  |  |  | 0
3.6 | Leachate collection tank | m3 | 6 | 150 | 2700 |  |  |  |  | 0
3.7 | Setting up a ground water well in the location shown | LS | 1 | 2500 | 2500 |  |  |  |  | 0
[5 empty] | 23899.7 |  |  |  |  | 0
4 | Concrete works | [8 empty] | 0
| Collection Bay Area | [8 empty] | 0
4.1 | Provide 100mm concrete floor screed for collection bay area according to the slope shown in drawing with a drain at the Sorting Area. Reinforcement for the slab shall be R6@150 BW single layer | m3 | 9.976 | 250 | 7485 |  |  |  |  | 0
4.2 | Wall Footing of Collection Bay Area walls cast according to drawing. Reinforcement shall be as shown on drawing | m3 | 2.9854 | 250 | 2242.5 |  |  |  |  | 0
4.3 | Middle Beams of Collection Bay Area walls cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 0.89561 | 250 | 675 |  |  |  |  | 0
4.4 | Lintel for Collection Bay Area walls cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 0.89561 | 250 | 675 |  |  |  |  | 0
4.5 | Columns for Collection Bay Area walls cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 1.3198 | 250 | 990 |  |  |  |  | 0
4.6 | Concrete column for sorting area platform cast according to drawing. | m3 | 0.612 | 250 | 459 |  |  | 459 |  | 0
4.7 | Provide 150mm thick reinforced concrete slab for sorting area platform cast according to drawing. Reinforcements shall be as shown on drawing. | m3 | 0.72 | 250 | 540 |  |  | 540 |  | 0
| Compost Slab | [6 empty] | 0 |  | 0
4.8 | Compost slab panels cast according to the slopes shown on drawing. Reinforcement shall be as shown on drawings. | m3 | 12 | 250 | 9000 | not as per drawing |  | 4500 |  | 0
4.9 | B1 beams of compost slab cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 1.989 | 250 | 1492.5 | not as per drawing |  | 746.25 |  | 0
4.1 | B2 beams of compost slab cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 0.639 | 250 | 480 | not as per drawing |  | 240 |  | 0
4.11 | B3 beams of compost slab with a mortar layer at an adequate slope, cast according to drawing. Reinforcement shall be as shown on drawing. Rate shall include reinforcement work, formwork, casting and mortar works. | m3 | 1.35 | 250 | 1012.5 | not as per drawing |  | 506.25 |  | 0
4.12 | Leachate collection tank with primary and secondary tanks as shown on drawing. Rate shall include all formwork, casting and placing of the tank | Nos | 1 | 250 | 250 | not as per drawing |  | 250 |  | 0
| Perimeter Wall | [8 empty] | 0
4.13 | Perimeter wall column | m3 | 2.3254 | 250 | 1747.5 |  |  |  |  | 0
4.14 | Perimeter wall beam | m3 | 3.0409 | 250 | 2280 |  |  |  |  | 0
| Other | [8 empty] | 0
4.15 | Foundation for flood light pole | m3 | 0.288 | 250 | 217.5 |  |  | 217.5 |  | 0
4.16 | Ground water well casting work | LS | 1 | 250 | 250 |  |  |  |  | 0
[5 empty] | 29796.5 |  |  |  |  | 0
5 | Structural steel works | [8 empty] | 0
| Collection Bay Area | [8 empty] | 0
5.1 | Provide 75mm G.I pipe as structural columns for collection bay area. Rate shall include all fixings at both ends of the pipe for necessary connections as shown on drawing | Nos | 10 | 250 | 2500 |  |  |  |  | 0
5.2 | Provide truss as shown on the drawing. Rate shall include all cuttings, weldings, applying of protective coating for welded joints, and setting up the truss | m | 8.15 | 250 | 2037.5 | not for equipment room |  | 509.375 |  | 0
| Perimeter Wall | [8 empty] | 0
5.3 | Perimeter fence using 50mm G.I pipe as shown on drawing. Rate shall include all cuttings, weldings, applying of protective coating for welded joints, and, setting up the fence. | m | 79.5 | 250 | 19875 |  |  |  |  | 0
| Other | [8 empty] | 0
5.4 | Perimeter fence using 50mm G.I pipe as shown on drawing. Rate shall include all cuttings, weldings, applying of protective coating for welded joints, and, setting up the fence. | m | 79.5 | 250 | 19875 |  |  |  |  | 0
5.5 | Provide 75mm G.I pipe as flood light fixing poles. Rate shall include installation charges as shown on drawing. | Nos | 2 | 2500 | 5000 |  |  | 5000 |  | 0
[5 empty] | 49287.5 |  |  |  |  | 0
6 | Masonry works | [8 empty] | 0
| Collection Bay Area walls of thickness 150mm | [8 empty] | 0
6.1 | 3500mm high walls for Collection Bay Walls | m3 | 20.2063 | 150 | 9094.5 |  |  |  |  | 0
6.2 | 1500mm high walls for Collection Bay section separation | m3 | 2.4 | 150 | 1080 |  |  |  |  | 0
| Perimeter walls of thickness 150mm | [8 empty] | 0
6.3 | 1000mm high wall for perimeter wall | m3 | 10.1362 | 150 | 4563 |  |  |  |  | 0
| Other | [8 empty] | 0
6.4 | 2000mm high walls of thickness 150mm for Pump House (1700mm high wall above ground level with 300mm below ground level) | m3 | 1.755 | 150 | 792 |  |  |  |  | 0
[5 empty] | 15529.5 |  |  |  |  | 0
7 | Plastering works | [8 empty] | 0
| Collection Bay Area | [8 empty] | 0
7.1 | 25mm plastering on 3500mm high walls for Collection Bay Outer Walls | m2 | 319.12 | 25 | 15956 |  |  |  |  | 0
7.2 | 25mm plastering on 1500mm high walls for Collection Bay section separation | m2 | 51.3 | 25 | 2565 |  |  |  |  | 0
| Perimeter Wall | [8 empty] | 0
7.3 | 25mm plastering on 1000mm wall for perimeter wall | m2 | 171.825 | 25 | 8591.5 |  |  |  |  | 0
| Other | [8 empty] | 0
7.4 | 2000mm high walls of thickness 150mm for Pump House (1700mm high wall above ground level with 300mm below ground level) | m2 | 12.58 | 25 | 629 |  |  |  |  | 0
[5 empty] | 27741.5 |  |  |  |  | 0
8 | Painting works | [8 empty] | 0
| Collection Bay Area Walls | [8 empty] | 0
8.1 | Apply emulsion paint coating on 3500mm high walls for Collection Bay Outer Walls | m2 | 319.12 | 60 | 38294.4 |  |  | 38294.4 |  | 0
8.2 | Apply emulsion paint coating on 1500mm high walls for Collection Bay section separation | m2 | 51.3 | 60 | 6156 |  |  | 6156 |  | 0
| Collection Bay Area Steel Members | [6 empty] | 0 |  | 0
8.3 | Apply emulsion paint coating on G.I columns of collection bay | LS | 1 | 500 | 500 |  |  | 500 |  | 0
8.4 | Apply emulsion paint coating on the roof trusses | LS | 1 | 500 | 500 |  |  | 500 |  | 0
8.5 | Apply paint coating on the metal sliding door of the Hazardous waste storage room | LS | 1 | 500 | 500 |  |  |  |  | 0
8.6 | Apply paint coating on the two metal folding doors of the equipment room | LS | 2 | 500 | 1000 |  |  | 1000 |  | 0
| Perimeter Wall | [6 empty] | 0 |  | 0
8.7 | Apply emulsion paint coating on 1000mm high wall for perimeter fence | m2 | 171.825 | 35 | 12028.1 |  |  | 12028.1 |  | 0
| Perimeter Wall Steel members | [6 empty] | 0 |  | 0
8.7 | Apply emulsion paint coating on G.I members of perimeter fence | LS | 1 | 2000 | 2000 |  |  | 2000 |  | 0
8.9 | Apply emulsion paint coating on G.I members and MS Sheets of gates | LS | 1 | 1000 | 1000 |  |  | 1000 |  | 0
| Other | [6 empty] | 0 |  | 0
8.1 | Apply paint coating on flood light pole | LS | 2 | 250 | 500 |  |  | 500 |  | 0
8.11 | Apply emulsion paint coating on the removable timber covers of the leachate collection tanks | LS | 2 | 250 | 500 |  |  | 500 |  | 0
8.12 | Apply emulsion paint coating on 2000mm high walls of thickness 150mm for Pump House (1700mm high wall above ground level with 300mm below ground level) | m2 | 12.58 | 65 | 1635.4 |  |  | 1635.4 |  | 0
| Existing Structure | [6 empty] | 0 |  | 0
8.13 | Apply emulsion paint coating on G.I columns of existing structure | LS | 1 | 500 | 500 |  |  | 500 |  | 0
8.14 | Apply emulsion paint coating on 2m high walls of the existing structure | m2 | 58.1 | 55 | 6391 |  |  | 6391 |  | 0
[5 empty] | 71504.9 |  |  |  |  | 0
9 | Roofing works | [8 empty] | 0
| Collection Bay Area | [8 empty] | 0
9.1 | Lysaght roofing sheet for collection bay area. Rate shall include all necessary laps, fastening, fixtures and sealing of joints | m2 | 111.36 | 85 | 18932.2 |  |  |  |  | 0
9.2 | Roof flashing. Rate shall include fastening and sealing of joints | m | 31.8 | 150 | 4770 |  |  |  |  | 0
9.3 | Timber beams - 150 x 75mm. Rate shall include for all fixing and joints. | m | 69.6 | 85 | 5916 |  |  |  |  | 0
9.4 | Timber rafters - 100 x 50mm. Rate shall include for all fixing and joints | m | 25.7778 | 150 | 3867 |  |  |  |  | 0
9.5 | Timber battens - 50 x 38mm. Rate shall include for all fixing and joints. | m | 38.6667 | 150 | 5800.5 |  |  |  |  | 0
| Other | [8 empty] | 0
9.6 | Lysaght roofing sheet for Pump House. Rate shall include all necessary laps, fastening, fixtures and sealing of joints | m2 | 4 | 500 | 4000 |  |  |  |  | 0
9.7 | Pump House Timber rafters - 100 x 50mm. Rate shall include for all fixing and joints | m | 4 | 268 | 1072 |  |  |  |  | 0
9.8 | Pump House Timber battens - 50 x 38mm. Rate shall include for all fixing and joints. | m | 6.6667 | 150 | 1000.5 |  |  |  |  | 0
[5 empty] | 45358.2 |  |  |  |  | 0
10 | Electrical works | [8 empty] | 0
| Collection Bay Area | [8 empty] | 0
10.1 | Provide 3 phase 13 A power sockets in equipment room. Rate shall include connection to circuit breaker and all necessary accessories | Nos | 4 | 150 | 600 |  |  | 600 |  | 0
10.2 | Provide 100W ceiling mount energy saving light in equipment room, provide the switches near circuit breaker inside the equipment room. Rate shall include connection to circuit breaker | Nos | 1 | 150 | 150 |  |  | 150 |  | 0
10.3 | Provide 100W ceiling mount energy saving light in hazardous waste storage room, provide the switches near circuit breaker inside the equipment room. Rate shall include connection to circuit breaker | Nos | 1 | 150 | 150 |  |  | 150 |  | 0
10.4 | Provide and mount a Ceiling fan inside the Equipment Room as indicated. Rate shall include provision of switch near the circuit breaker inside the equipment room, connection to circuit breaker and all necessary accessories | Nos | 1 | 150 | 1500 |  |  | 1500 |  | 0
10.5 | Supply and fix electric meter, 4 pole MCCB, Single Phase distribution board and 3 Phase distribution board as shown on drawing. Earth link and connection to earth rod with proper earth pit should be provided as well | LS | 1 | 2500 | 2500 |  |  | 2500 |  | 0
10.6 | Provide and mount a exhaust fan inside the Equipment Room and Hazardous Waste Storage Room. Rate shall include provision of switch near the circuit breaker inside the equipment room, connection to circuit breaker and all necessary accessories | LS | 2 | 500 | 1000 |  |  | 1000 |  | 0
10.7 | Provide weather proof switch for all lights | LS | 1 |  |  |  |  | 0 |  | 0
10.8 | Provide 25 sqmm 4 core power supply cable from nearest distribution box to waste yard distribution board | m | 150 | 125 | 18750 |  |  | 18750 |  | 0
| Other | [6 empty] | 0 |  | 0
10.9 | Provide 13 A power socket for well water pump inside the Pump House, provide the switch for the pump near circuit breaker inside the equipment room. Rate shall include connection to circuit breaker. | Nos | 1 | 150 | 150 |  |  | 150 |  | 0
10.1 | Provide 200 W flood light for illuminating the waste yard. Rate shall include connecting each light to a switch near circuit breaker inside the equipment roomand providing power to the switch | Nos | 2 | 150 | 300 |  |  | 300 |  | 0
10.11 | Provide well water pump. Rate shall include its fixing inside the Pump House | Nos | 1 | 2500 | 2500 |  |  | 2500 |  | 0
[5 empty] | 27600 |  |  |  |  | 0
11 | Plumbing works | [8 empty] | 0
11.1 | Provide connection from pump to ground water well. Rate shall include all necessary pipes, bends, fittings and footvalve and others as maybe required. | LS | 1 | 500 | 500 |  |  | 500 |  | 0
11.2 | Provide outlet pipes as shown on drawing. Rate shall include connection to pump, bends, fittings and others as maybe necessary. | LS | 1 | 1000 | 1000 |  |  | 1000 |  | 0
11.3 | Provide PVC taps at ends of outlet pipes. | Nos | 2 | 500 | 1000 | no tap |  | 500 |  | 0
11.4 | Supply 25mm diameter flexible hose | m | 25 | 85 | 2125 |  |  | 2125 |  | 0
[5 empty] | 4625 |  |  |  |  | 0
12 | Doors and windows | [8 empty] | 0
| Metal Doors | [8 empty] | 0
12.1 | Provide lockable metal sliding gates for entrance to hazardous waste storage room. Rate shall include all cuts, welds, applying protective coating to welded joints, painting the door and proper fixing of the door. Rate shall include fabrication and fixing of guide rails and wheels as well. | Nos | 1 | 5000 | 5000 |  |  |  |  | 0
12.2 | Provide lockable metal folding gates for entrance to Equipment room. Rate shall include all cuts, welds, applying protective coating to welded joints, painting the door and proper fixing of the door. Rate shall include fabrication and fixing of guide rails and wheels as well. | Nos | 2 | 2500 | 5000 |  |  | 5000 |  | 0
12.3 | Provide lockable metal gates for entrance to waste yard as specified in the drawing. Rate shall include all cuts, welds, applying protective coating to welded joints, painting the frame and properly fixing the door to the fence. | Nos | 2 | 5000 | 5000 |  |  | 5000 |  | 0
| Timber Doors | [6 empty] | 0 |  | 0
12.4 | Provide a lockable timber door of dimensions 1000mm x 1000mm with double door frames and fixed timber louvers for the ground water pump room hut. Rates shall include all materials, hinges and fixings. | Nos | 1 | 1500 | 1500 |  |  | 1500 |  | 0
[5 empty] | 16500 |  |  |  |  | 0
13 | Other Works | [8 empty] | 0
| Collection Bay Area | [8 empty] | 0
13.1 | Provide a 5" vinyl roof gutter with 2" x 3" downspout. Rates shall include all materials and fastenings. | LS | 1 | 500 | 500 |  |  | 500 |  | 0
13.2 | Provide 12" x 12" ceramic tiles for the top and the sides of the concrete slab for sorting area platform | m2 | 6.6 | 250 | 3300 |  |  | 3300 |  | 0
| Perimeter Wall | [8 empty] | 0
13.3 | 50 x 50 PVC coated mesh. Rate shall include properly securing the mesh to G.I steel frame | m2 | 166.95 | 55 | 18364.5 |  |  | 18364.5 |  | 0
| Compost Slab | [8 empty] | 0
13.4 | Provide HDPE membrane below compost slab, Concrete screed and collection bay floor slab | m2 | 219.76 | 25 | 10980 |  |  |  |  | 0
13.5 | Provide expansion joint in slab and fill the joint with polyethylene joint filler form and silicone as shown on drawing | m | 24 | 250 | 6000 |  |  |  |  | 0
13.6 | Provide two timber removable covers for the leachate collection tank of size 1000x2000mm. Rates shall include all materials, fastenings and handles. | LS | 2 | 500 | 1000 |  |  | 1000 |  | 0
13.7 | Connection of compost slab drain to primary tank of the leachate tank including ball valve | LS | 1 | 890 | 890 | need to be fixed |  | 445 |  | 0
[5 empty] | 41034.5 |  |  |  |  | 0
14 | Demobilisation Works | [8 empty] | 0
14.1 | Setup sign boards on site as specified | LS | 1 | 500 | 500 |  |  | 500 |  | 0
14.2 | Clean up site upon completion of works | LS | 1 | 2500 | 2500 |  |  | 2500 |  | 0
14.3 | Demobilization | LS | 1 | 2500 | 2500 |  |  | 2500 |  | 0
[5 empty] | 5500 |  | Incomplete Works | 160007.775 |  | 12450
|  |  |  | 378577.3 | 381277.3
|  |  |  | 22714.638 | 22876.638
|  |  | Actual Price | 401291.938 | 404153.938
|  |  | Variation | 68688
469979.938

## CW at TR
CONSTRUCTION OF WASTE MANAGEMENT CENTRE - GA. NILANDHOO
Bill of Quantities
| Length of Collection Bay Area | 23.2
| Width of Collection Bay Area | 4.3
| Total length of Collection Bay Area 3.5m high walls | 41.9
| Number of G.I Pipe Columns in Collection Bay Area | 10
| Number of RC Columns in Collection Bay Area | 13.9667
| Total length of Collection Bay Area 1.5m high walls | 16
| Total length of Perimeter Wall | 79.5
| Number of Columns in Perimeter Wall | 39.75
| Length of Compost Slab | 15
| Width of Compost Slab | 8
| Length of Concrete Screed | 0
| Width of Concrete Screed | 0
Completed at termination
No | Item | Unit | Quantity | Rate | Rate based on amount | Amount | [5 empty] | Qty | Amount
1 | Preliminaries
1.1 | Mobilization to site | LS | 1 | 5000 | 5000 | 5000 | 5000 | 0 |  |  |  | 1 | 5000 |  | 100%
1.2 | Site management cost including set up of temporary services for contractor's services as maybe necessary | LS | 1 | 2500 | 2500 | 2500 | 2500 | 0 |  |  |  | 0.5 | 1250 |  | 50%
[6 empty] | 7500 | 0 | [5 empty] | 0
2 | Site Clearance and Demolition/Removal | [5 empty] | 0 | 0 |  |  |  |  | 0
2.1 | All site clean up work including relocation of existing waste to a temporary location identified by island council | LS | 1 | 2500 | 2500 | 2500 | 2500 | 0 |  |  |  | 1 | 2500 |  | 100%
| Demolition | [5 empty] | 0 | 0 |  |  |  |  | 0
2.2 | Concrete column foundation 450x450mm of height 400mm | LS | 20 | 250 | 250 | 5000 | 5000 | 0 |  |  |  | 20 | 5000 |  | 100%
2.3 | 2000mm high masonry walls | m | 7.4 | 500 | 500 | 3700 | 3700 | 0 |  |  | 3700 | 7.4 | 3700 |  | 100%
| Removal | [5 empty] | 0 | 0 |  |  |  |  | 0
2.4 | G.I Pipe fence of height 2000mm with 50mm Mesh as shown in the drawing | m | 60 | 25 | 25 | 1500 | 1500 | 0 |  |  |  | 60 | 1500 |  | 100%
[6 empty] | 12700 | 0 | [5 empty] | 0
3 | Earth works | [5 empty] | 0 | 0 |  |  |  |  | 0
| Allow for all excavation work for foundations as follows | [5 empty] | 0 | 0 |  |  |  |  | 0
3.1 | Collection bay foundation | m3 | 4.8945 | 150 | 449.5863 | 2200.5 | 734.175 | -1466.325 |  |  |  | 4.8945 | 2200.5 |  | 100%
3.2 | Perimeter wall | m3 | 8.3475 | 150 | 450.1348 | 3757.5 | 1252.125 | -2505.375 |  |  |  | 8.3475 | 3757.5 |  | 100%
3.4 | Flood light pole | m3 | 0.128 | 150 | 457.0312 | 58.5 | 19.2 | -39.3 |  |  |  | 0 | 0 |  | 0%
3.5 | Ground levelling works for ground slab works | m2 | 219.76 | 35 | 70 | 15383.2 | 7691.6 | -7691.6 |  |  |  | 219.76 | 15383.2 |  | 100%
3.6 | Leachate collection tank | m3 | 6 | 150 | 450 | 2700 | 900 | -1800 |  |  |  | 6 | 2700 |  | 100%
3.7 | Setting up a ground water well in the location shown | LS | 1 | 2500 | 2500 | 2500 | 2500 | 0 |  |  |  | 1 | 2500 |  | 100%
[6 empty] | 23899.7 | 0 | [5 empty] | 0
4 | Concrete works | [5 empty] | 0 | 0 |  |  |  |  | 0
| Collection Bay Area | [5 empty] | 0 | 0 |  |  |  |  | 0 | ** floor of equipment room without any slope at the entrance. Could be difficult to setup the equipments inside the room.
4.1 | Provide 100mm concrete floor screed for collection bay area according to the slope shown in drawing with a drain at the Sorting Area. Reinforcement for the slab shall be R6@150 BW single layer | m3 | 9.976 | 250 | 750.3007 | 7485 | 2494 | -4991 |  |  |  | 9.976 | 7485 | NO slope, no drain. | 100%
4.2 | Wall Footing of Collection Bay Area walls cast according to drawing. Reinforcement shall be as shown on drawing | m3 | 2.9854 | 250 | 751.1619 | 2242.5 | 746.3438 | -1496.1562 |  |  |  | 2.9854 | 2242.5 |  | 100%
4.3 | Middle Beams of Collection Bay Area walls cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 0.89561 | 250 | 753.6742 | 675 | 223.9031 | -451.0969 |  |  |  | 0.89561 | 675 |  | 100%
4.4 | Lintel for Collection Bay Area walls cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 0.89561 | 250 | 753.6742 | 675 | 223.9031 | -451.0969 |  |  |  | 0.89561 | 675 |  | 100%
4.5 | Columns for Collection Bay Area walls cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 1.3198 | 250 | 750.0852 | 990 | 329.9625 | -660.0375 |  |  |  | 1.3198 | 990 |  | 100%
4.6 | Concrete column for sorting area platform cast according to drawing. | m3 | 0.612 | 250 | 750 | 459 | 153 | -306 |  |  | 459 | 0 | 0 | 0% completed | 0%
4.7 | Provide 150mm thick reinforced concrete slab for sorting area platform cast according to drawing. Reinforcements shall be as shown on drawing. | m3 | 0.72 | 250 | 750 | 540 | 180 | -360 |  |  | 540 | 0 | 0 | 0% completed | 0%
| Compost Slab | [5 empty] | 0 | 0 |  |  | 0 |  | 0
4.8 | Compost slab panels cast according to the slopes shown on drawing. Reinforcement shall be as shown on drawings. | m3 | 12 | 250 | 750 | 9000 | 3000 | -6000 | not as per drawing |  | 4500 |  | 0 | Issue with slope of the compost slab. Slope has to be fixed, so that the water will slope straight to the drain. Currently water flows sideways to the ground. | 0%
4.9 | B1 beams of compost slab cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 1.989 | 250 | 750.3771 | 1492.5 | 497.25 | -995.25 | not as per drawing |  | 746.25 | 1.989 | 1492.5 | Issue with slope of the compost slab. Slope has to be fixed, so that the water will slope straight to the drain. Currently water flows sideways to the ground. | 100%
4.1 | B2 beams of compost slab cast according to drawing. Reinforcement shall be as shown on drawing. | m3 | 0.639 | 250 | 751.1737 | 480 | 159.75 | -320.25 | not as per drawing |  | 240 | 0.639 | 480 | Issue with slope of the compost slab. Slope has to be fixed, so that the water will slope straight to the drain. Currently water flows sideways to the ground. | 100%
4.11 | B3 beams of compost slab with a mortar layer at an adequate slope, cast according to drawing. Reinforcement shall be as shown on drawing. Rate shall include reinforcement work, formwork, casting and mortar works. | m3 | 1.35 | 250 | 750 | 1012.5 | 337.5 | -675 | not as per drawing |  | 506.25 |  | 0 | Issue with slope of the B3 beam. Slope of the drain has to be fixed, so that the water will slope straight to the leachat tank. Slope not connected to leachat tank. | 0%
4.12 | Leachate collection tank with primary and secondary tanks as shown on drawing. Rate shall include all formwork, casting and placing of the tank | Nos | 1 | 250 | 250 | 250 | 250 | 0 | not as per drawing |  | 250 |  | 0 | Top of the leachate tank fully covered with contreate sheet. According to the drawing both tanks should have a removable timber cover. Both Primary and secondary tanks are in same size. | 0%
| Perimeter Wall | [5 empty] | 0 | 0 |  |  |  |  | 0
4.13 | Perimeter wall column | m3 | 2.3254 | 250 | 751.4917 | 1747.5 | 581.3437 | -1166.1562 |  |  |  | 2.3254 | 1747.5 |  | 100%
4.14 | Perimeter wall beam | m3 | 3.0409 | 250 | 749.7842 | 2280 | 760.2188 | -1519.7812 |  |  |  | 3.0409 | 2280 |  | 100%
| Other | [5 empty] | 0 | 0 |  |  |  |  | 0
4.15 | Foundation for flood light pole | m3 | 0.288 | 250 | 755.2083 | 217.5 | 72 | -145.5 |  |  | 217.5 | 0 | 0 |  | 0%
4.16 | Ground water well casting work | LS | 1 | 250 | 250 | 250 | 250 | 0 |  |  |  | 1 | 250 |  | 100%
[6 empty] | 29796.5 | 0 | [5 empty] | 0
5 | Structural steel works | [5 empty] | 0 | 0 |  |  |  |  | 0
| Collection Bay Area | [5 empty] | 0 | 0 |  |  |  |  | 0
5.1 | Provide 75mm G.I pipe as structural columns for collection bay area. Rate shall include all fixings at both ends of the pipe for necessary connections as shown on drawing | Nos | 10 | 250 | 250 | 2500 | 2500 | 0 |  |  |  |  | 0 | G.I pipes not completed. Refer "Collection Bay - Floor Plan" | 0%
5.2 | Provide truss as shown on the drawing. Rate shall include all cuttings, weldings, applying of protective coating for welded joints, and setting up the truss | m | 8.15 | 250 | 250 | 2037.5 | 2037.5 | 0 | not for equipment room |  | 509.375 |  | 0 | No truss in equipment room. Instead of a truss there is a concrete beam. This could make it difficult to setup the equipments inside the room. | 0%
| Perimeter Wall | [5 empty] | 0 | 0 |  |  |  |  | 0
5.3 | Perimeter fence using 50mm G.I pipe as shown on drawing. Rate shall include all cuttings, weldings, applying of protective coating for welded joints, and, setting up the fence. | m | 79.5 | 250 | 250 | 19875 | 19875 | 0 |  |  |  | 77.5 | 19375 | 2m x 3qty of G.I pipe not welded. | 97.48% |  | 0.97484
| Other | [5 empty] | 0 | 0 |  |  |  |  | 0
5.4 | Perimeter fence using 50mm G.I pipe as shown on drawing. Rate shall include all cuttings, weldings, applying of protective coating for welded joints, and, setting up the fence. | m | 79.5 | 250 | 250 | 19875 | 19875 | 0 |  |  |  | 0 | 0 | I think this is repeat of 5.3 :'( | 0%
5.5 | Provide 75mm G.I pipe as flood light fixing poles. Rate shall include installation charges as shown on drawing. | Nos | 2 | 2500 | 2500 | 5000 | 5000 | 0 |  |  | 5000 | 0 | 0 |  | 0%
[6 empty] | 49287.5 | 0 | [5 empty] | 0
6 | Masonry works | [5 empty] | 0 | 0 |  |  |  |  | 0
| Collection Bay Area walls of thickness 150mm | [5 empty] | 0 | 0 |  |  |  |  | 0
6.1 | 3500mm high walls for Collection Bay Walls | m3 | 20.2063 | 150 | 450.083 | 9094.5 | 3030.9412 | -6063.5588 |  |  |  | 20.2063 | 9094.5 |  | 100%
6.2 | 1500mm high walls for Collection Bay section separation | m3 | 2.4 | 150 | 450 | 1080 | 360 | -720 |  |  |  | 2.4 | 1080 |  | 100%
| Perimeter walls of thickness 150mm | [5 empty] | 0 | 0 |  |  |  |  | 0
6.3 | 1000mm high wall for perimeter wall | m3 | 10.1362 | 150 | 450.1665 | 4563 | 1520.4375 | -3042.5625 |  |  |  | 10.1362 | 4563 |  | 100%
| Other | [5 empty] | 0 | 0 |  |  |  |  | 0
6.4 | 2000mm high walls of thickness 150mm for Pump House (1700mm high wall above ground level with 300mm below ground level) | m3 | 1.755 | 150 | 451.2821 | 792 | 263.25 | -528.75 |  |  |  | 1.755 | 792 |  | 100%
[6 empty] | 15529.5 | 0 | [5 empty] | 0
7 | Plastering works | [5 empty] | 0 | 0 |  |  |  |  | 0
| Collection Bay Area | [5 empty] | 0 | 0 |  |  |  |  | 0
7.1 | 25mm plastering on 3500mm high walls for Collection Bay Outer Walls | m2 | 319.12 | 25 | 50 | 15956 | 7978 | -7978 |  |  |  | 319.12 | 15956 |  | 100%
7.2 | 25mm plastering on 1500mm high walls for Collection Bay section separation | m2 | 51.3 | 25 | 50 | 2565 | 1282.5 | -1282.5 |  |  |  | 51.3 | 2565 |  | 100%
| Perimeter Wall | [5 empty] | 0 | 0 |  |  |  |  | 0
7.3 | 25mm plastering on 1000mm wall for perimeter wall | m2 | 171.825 | 25 | 50.0015 | 8591.5 | 4295.625 | -4295.875 |  |  |  | 171.825 | 8591.5 |  | 100%
| Other | [5 empty] | 0 | 0 |  |  |  |  | 0
7.4 | 2000mm high walls of thickness 150mm for Pump House (1700mm high wall above ground level with 300mm below ground level) | m2 | 12.58 | 25 | 50 | 629 | 314.5 | -314.5 |  |  |  | 12.58 | 629 |  | 100%
[6 empty] | 27741.5 | 0 | [5 empty] | 0
8 | Painting works | [5 empty] | 0 | 0 |  |  |  |  | 0
| Collection Bay Area Walls | [5 empty] | 0 | 0 |  |  |  |  | 0
8.1 | Apply emulsion paint coating on 3500mm high walls for Collection Bay Outer Walls | m2 | 319.12 | 60 | 120 | 38294.4 | 19147.2 | -19147.2 |  |  | 38294.4 | 0 | 0 | painting not completed | 0%
8.2 | Apply emulsion paint coating on 1500mm high walls for Collection Bay section separation | m2 | 51.3 | 60 | 120 | 6156 | 3078 | -3078 |  |  | 6156 | 0 | 0 | painting not completed | 0%
| Collection Bay Area Steel Members | [5 empty] | 0 | 0 |  |  | 0 |  | 0
8.3 | Apply emulsion paint coating on G.I columns of collection bay | LS | 1 | 500 | 500 | 500 | 500 | 0 |  |  | 500 | 0.36364 | 181.8182 | painting 7/11 not completed | 36.36%
8.4 | Apply emulsion paint coating on the roof trusses | LS | 1 | 500 | 500 | 500 | 500 | 0 |  |  | 500 | 0 | 0 | painting not completed in the equipment room | 0%
8.5 | Apply paint coating on the metal sliding door of the Hazardous waste storage room | LS | 1 | 500 | 500 | 500 | 500 | 0 |  |  |  | 1 | 500 |  | 100%
8.6 | Apply paint coating on the two metal folding doors of the equipment room | LS | 2 | 500 | 500 | 1000 | 1000 | 0 |  |  | 1000 | 0 | 0 | painting not completed (no door fixed) | 0%
| Perimeter Wall | [5 empty] | 0 | 0 |  |  | 0 |  | 0
8.7 | Apply emulsion paint coating on 1000mm high wall for perimeter fence | m2 | 171.825 | 35 | 70.002 | 12028.1 | 6013.875 | -6014.225 |  |  | 12028.1 | 0 | 0 | 0% completed | 0%
| Perimeter Wall Steel members | [5 empty] | 0 | 0 |  |  | 0 |  | 0
8.7 | Apply emulsion paint coating on G.I members of perimeter fence | LS | 1 | 2000 | 2000 | 2000 | 2000 | 0 |  |  | 2000 | 0.97484 | 1949.6855 | completed except for the 2m x 3qty of G.I pipe not welded. | 97.48%
8.9 | Apply emulsion paint coating on G.I members and MS Sheets of gates | LS | 1 | 1000 | 1000 | 1000 | 1000 | 0 |  |  | 1000 | 0 | 0 | no gate. No painting | 0%
| Other | [5 empty] | 0 | 0 |  |  | 0 |  | 0
8.1 | Apply paint coating on flood light pole | LS | 2 | 250 | 250 | 500 | 500 | 0 |  |  | 500 | 0 | 0 | 0% completed | 0%
8.11 | Apply emulsion paint coating on the removable timber covers of the leachate collection tanks | LS | 2 | 250 | 250 | 500 | 500 | 0 |  |  | 500 | 0 | 0 | No timber cover, no painting | 0%
8.12 | Apply emulsion paint coating on 2000mm high walls of thickness 150mm for Pump House (1700mm high wall above ground level with 300mm below ground level) | m2 | 12.58 | 65 | 130 | 1635.4 | 817.7 | -817.7 |  |  | 1635.4 | 0 | 0 | 0% completed | 0%
| Existing Structure | [5 empty] | 0 | 0 |  |  | 0 |  | 0
8.13 | Apply emulsion paint coating on G.I columns of existing structure | LS | 1 | 500 | 500 | 500 | 500 | 0 |  |  | 500 | 0 | 0 |  | 0%
8.14 | Apply emulsion paint coating on 2m high walls of the existing structure | m2 | 58.1 | 55 | 110 | 6391 | 3195.5 | -3195.5 |  |  | 6391 | 0 | 0 | 0% completed | 0%
[6 empty] | 71504.9 | 0 | [5 empty] | 0
9 | Roofing works | [5 empty] | 0 | 0 |  |  |  |  | 0
| Collection Bay Area | [5 empty] | 0 | 0 |  |  |  |  | 0
9.1 | Lysaght roofing sheet for collection bay area. Rate shall include all necessary laps, fastening, fixtures and sealing of joints | m2 | 111.36 | 85 | 170.009 | 18932.2 | 9465.6 | -9466.6 |  |  |  | 111.36 | 18932.2 |  | 100%
9.2 | Roof flashing. Rate shall include fastening and sealing of joints | m | 31.8 | 150 | 150 | 4770 | 4770 | 0 |  |  |  | 0 | 0 | 0% completed | 0%
9.3 | Timber beams - 150 x 75mm. Rate shall include for all fixing and joints. | m | 69.6 | 85 | 85 | 5916 | 5916 | 0 |  |  |  | 46.4 | 3944 | 2 beams fixed | 66.67%
9.4 | Timber rafters - 100 x 50mm. Rate shall include for all fixing and joints | m | 25.7778 | 150 | 150.0129 | 3867 | 3866.6667 | -0.33333 |  |  |  | 25.7778 | 3867 |  | 100%
9.5 | Timber battens - 50 x 38mm. Rate shall include for all fixing and joints. | m | 38.6667 | 150 | 150.0129 | 5800.5 | 5800 | -0.5 |  |  |  | 38.6667 | 5800.5 |  | 100% | 166.2667 |  | 116
| Other | [5 empty] | 0 | 0 |  |  |  |  | 0
9.6 | Lysaght roofing sheet for Pump House. Rate shall include all necessary laps, fastening, fixtures and sealing of joints | m2 | 4 | 500 | 1000 | 4000 | 2000 | -2000 |  |  |  | 4 | 4000 |  | 100%
9.7 | Pump House Timber rafters - 100 x 50mm. Rate shall include for all fixing and joints | m | 4 | 268 | 268 | 1072 | 1072 | 0 |  |  |  | 4 | 1072 |  | 100%
9.8 | Pump House Timber battens - 50 x 38mm. Rate shall include for all fixing and joints. | m | 6.6667 | 150 | 150.075 | 1000.5 | 1000 | -0.5 |  |  |  | 6.6667 | 1000.5 |  | 100%
[6 empty] | 45358.2 | 0 | [5 empty] | 0
10 | Electrical works | [5 empty] | 0 | 0 |  |  |  |  | 0
| Collection Bay Area | [5 empty] | 0 | 0 |  |  |  |  | 0
10.1 | Provide 3 phase 13 A power sockets in equipment room. Rate shall include connection to circuit breaker and all necessary accessories | Nos | 4 | 150 | 150 | 600 | 600 | 0 |  |  | 600 | 0 | 0 | No power sockets. Connection cables partly done. Unable to verify electricty work done. | 0%
10.2 | Provide 100W ceiling mount energy saving light in equipment room, provide the switches near circuit breaker inside the equipment room. Rate shall include connection to circuit breaker | Nos | 1 | 150 | 150 | 150 | 150 | 0 |  |  | 150 | 0 | 0 | no light. Connection cables partly done. Unable to verify electricty work done. | 0%
10.3 | Provide 100W ceiling mount energy saving light in hazardous waste storage room, provide the switches near circuit breaker inside the equipment room. Rate shall include connection to circuit breaker | Nos | 1 | 150 | 150 | 150 | 150 | 0 |  |  | 150 | 0 | 0 | no light. No cable. | 0%
10.4 | Provide and mount a Ceiling fan inside the Equipment Room as indicated. Rate shall include provision of switch near the circuit breaker inside the equipment room, connection to circuit breaker and all necessary accessories | Nos | 1 | 150 | 1500 | 1500 | 150 | -1350 |  |  | 1500 | 0 | 0 | no fan. No wiring. | 0%
10.5 | Supply and fix electric meter, 4 pole MCCB, Single Phase distribution board and 3 Phase distribution board as shown on drawing. Earth link and connection to earth rod with proper earth pit should be provided as well | LS | 1 | 2500 | 2500 | 2500 | 2500 | 0 |  |  | 2500 | 0 | 0 | no D.Board. | 0%
10.6 | Provide and mount a exhaust fan inside the Equipment Room and Hazardous Waste Storage Room. Rate shall include provision of switch near the circuit breaker inside the equipment room, connection to circuit breaker and all necessary accessories | LS | 2 | 500 | 500 | 1000 | 1000 | 0 |  |  | 1000 | 0 | 0 | connection to circuit breaker to fixed. | 0%
10.7 | Provide weather proof switch for all lights | LS | 1 |  | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | Switch not fixed | 0%
10.8 | Provide 25 sqmm 4 core power supply cable from nearest distribution box to waste yard distribution board | m | 150 | 125 | 125 | 18750 | 18750 | 0 |  |  | 18750 | 0 | 0 | no power supply cable. | 0%
| Other | [5 empty] | 0 | 0 |  |  | 0 |  | 0
10.9 | Provide 13 A power socket for well water pump inside the Pump House, provide the switch for the pump near circuit breaker inside the equipment room. Rate shall include connection to circuit breaker. | Nos | 1 | 150 | 150 | 150 | 150 | 0 |  |  | 150 | 0 | 0 | no socket no connection | 0%
10.1 | Provide 200 W flood light for illuminating the waste yard. Rate shall include connecting each light to a switch near circuit breaker inside the equipment roomand providing power to the switch | Nos | 2 | 150 | 150 | 300 | 300 | 0 |  |  | 300 | 0 | 0 | no flood light | 0%
10.11 | Provide well water pump. Rate shall include its fixing inside the Pump House | Nos | 1 | 2500 | 2500 | 2500 | 2500 | 0 |  |  | 2500 | 0 | 0 | no well water pump | 0%
[6 empty] | 27600 | 0 | [5 empty] | 0
11 | Plumbing works | [5 empty] | 0 | 0 |  |  |  |  | 0
11.1 | Provide connection from pump to ground water well. Rate shall include all necessary pipes, bends, fittings and footvalve and others as maybe required. | LS | 1 | 500 | 500 | 500 | 500 | 0 |  |  | 500 |  | 0 | no connection | 0%
11.2 | Provide outlet pipes as shown on drawing. Rate shall include connection to pump, bends, fittings and others as maybe necessary. | LS | 1 | 1000 | 1000 | 1000 | 1000 | 0 |  |  | 1000 |  | 0 | Outlet pipe fixed. unable to verify the connection. | 0%
11.3 | Provide PVC taps at ends of outlet pipes. | Nos | 2 | 500 | 500 | 1000 | 1000 | 0 | no tap |  | 500 | 0 | 0 | no tap | 0%
11.4 | Supply 25mm diameter flexible hose | m | 25 | 85 | 85 | 2125 | 2125 | 0 |  |  | 2125 |  | 0 | no hose | 0%
[6 empty] | 4625 | 0 | [5 empty] | 0
12 | Doors and windows | [5 empty] | 0 | 0 |  |  |  |  | 0
| Metal Doors | [5 empty] | 0 | 0 |  |  |  |  | 0
12.1 | Provide lockable metal sliding gates for entrance to hazardous waste storage room. Rate shall include all cuts, welds, applying protective coating to welded joints, painting the door and proper fixing of the door. Rate shall include fabrication and fixing of guide rails and wheels as well. | Nos | 1 | 5000 | 5000 | 5000 | 5000 | 0 | no lock |  |  | 0.9 | 4500 | sliding gates fixed, but not lockable. | 90%
12.2 | Provide lockable metal folding gates for entrance to Equipment room. Rate shall include all cuts, welds, applying protective coating to welded joints, painting the door and proper fixing of the door. Rate shall include fabrication and fixing of guide rails and wheels as well. | Nos | 2 | 2500 | 2500 | 5000 | 5000 | 0 |  |  | 5000 | 0 | 0 | 0% completed | 0%
12.3 | Provide lockable metal gates for entrance to waste yard as specified in the drawing. Rate shall include all cuts, welds, applying protective coating to welded joints, painting the frame and properly fixing the door to the fence. | Nos | 2 | 5000 | 2500 | 5000 | 10000 | 5000 |  |  | 5000 |  | 0 | 0% completed | 0%
| Timber Doors | [5 empty] | 0 | 0 |  |  | 0 |  | 0
12.4 | Provide a lockable timber door of dimensions 1000mm x 1000mm with double door frames and fixed timber louvers for the ground water pump room hut. Rates shall include all materials, hinges and fixings. | Nos | 1 | 1500 | 1500 | 1500 | 1500 | 0 |  |  | 1500 | 0 | 0 | 0% completed | 0%
[6 empty] | 16500 | 0 | [5 empty] | 0
13 | Other Works | [5 empty] | 0 | 0 |  |  |  |  | 0
| Collection Bay Area | [5 empty] | 0 | 0 |  |  |  |  | 0
13.1 | Provide a 5" vinyl roof gutter with 2" x 3" downspout. Rates shall include all materials and fastenings. | LS | 1 | 500 | 500 | 500 | 500 | 0 |  |  | 500 | 0 | 0 | 0% completed | 0%
13.2 | Provide 12" x 12" ceramic tiles for the top and the sides of the concrete slab for sorting area platform | m2 | 6.6 | 250 | 500 | 3300 | 1650 | -1650 |  |  | 3300 |  | 0 | 0% completed | 0%
| Perimeter Wall | [5 empty] | 0 | 0 |  |  |  |  | 0
13.3 | 50 x 50 PVC coated mesh. Rate shall include properly securing the mesh to G.I steel frame | m2 | 166.95 | 55 | 110 | 18364.5 | 9182.25 | -9182.25 |  |  | 18364.5 | 0 | 0 | 0% completed | 0%
| Compost Slab | [5 empty] | 0 | 0 |  |  |  |  | 0
13.4 | Provide HDPE membrane below compost slab, Concrete screed and collection bay floor slab | m2 | 219.76 | 25 | 49.9636 | 10980 | 5494 | -5486 |  |  |  | 219.76 | 10980 |  | 100%
13.5 | Provide expansion joint in slab and fill the joint with polyethylene joint filler form and silicone as shown on drawing | m | 24 | 250 | 250 | 6000 | 6000 | 0 |  |  |  | 24 | 6000 |  | 100%
13.6 | Provide two timber removable covers for the leachate collection tank of size 1000x2000mm. Rates shall include all materials, fastenings and handles. | LS | 2 | 500 | 500 | 1000 | 1000 | 0 |  |  | 1000 | 0 | 0 | 0% completed | 0%
13.7 | Connection of compost slab drain to primary tank of the leachate tank including ball valve | LS | 1 | 890 | 890 | 890 | 890 | 0 | need to be fixed |  | 445 | 0 | 0 | ** Overfloor pipe in leachate tank need to be fixed. Connection is placed lower than the specified location in the drawing. ** Unable to verify the connection from compost slap to primary tank | 0%
[6 empty] | 41034.5 | 0 | [5 empty] | 0
14 | Demobilisation Works | [5 empty] | 0 | 0 |  |  |  |  | 0
14.1 | Setup sign boards on site as specified | LS | 1 | 500 | 500 | 500 | 500 | 0 |  |  | 500 | 0 | 0 | 0% completed | 0%
14.2 | Clean up site upon completion of works | LS | 1 | 2500 | 2500 | 2500 | 2500 | 0 |  |  | 2500 | 0 | 0 | 0% completed | 0%
14.3 | Demobilization | LS | 1 | 2500 | 2500 | 2500 | 2500 | 0 |  |  | 2500 | 0 | 0 | 0% completed | 0%
[6 empty] | 5500 | 248922.8204 |  |  | Incomplete Works | 160007.775
|  |  |  | 378577.3 |  | 381277.3 | [6 empty] | 189182.4037 |  | 49.62%
| GST | [11 empty] | 11350.9442
| Total Engineer Certified Value | [11 empty] | 200533.3479
| Total Contract Value |  |  |  |  | 469979.94
| LD 15% |  |  |  |  | 70496.991
| Value of works completed - Engineer Approved |  |  |  |  | 200533.3479
| (-) Retention [5% from value of work completed (Engineer Approved)] |  |  |  |  | 10026.6674
| Value after Retention |  |  |  |  | 190506.6805
| (-) Liquidate Damage [15% of total contract value] |  |  |  |  | 70496.991
| Total Payments Issued to the contractor |  |  |  |  | 224521.682
| Paybale/(Receivable) |  |  |  |  | -104511.9925